## Slide 1: 🔥 ADO Usage (Hands-On)

## Slide 2: Week 7 • Day 2 • Agile Delivery & ADO Mastery
TPM Academy
Notes: Bring your laptop. Today: load your feature into ADO with disciplined hierarchy, fields, queries.

## Slide 3: 🎯 Day 2 Objectives
Use the 4-level hierarchy (Epic → Feature → User Story → Task) without going deeper
Apply field discipline to every work item
Estimate with story points; split anything >13
Build the 5 essential queries + sprint board + Kanban board
Read the 3 standard charts: cumulative flow diagram (CFD), burn-down, velocity
Use AI as a standup-prep aid — with validation
Notes: By 16:00, every quad has DP Section 2 with loaded ADO + queries + boards.

## Slide 4: 🕑 Today’s Shape
Clock
Block
Outcome
09:00 – 09:15
Opening
ADO access check; pin DP Section 1
09:15 – 10:30
Block 1 + Activity 1
Build the hierarchy
10:45 – 12:00
Block 2 + Activity 2
Field discipline + Tasks
13:00 – 14:15
Block 3 + Activity 3
Queries + Boards
14:30 – 16:00
Block 4 + Activity 4 + Wrap
Charts + AI standup aid
Notes: Heaviest hands-on day of the week.

## Slide 5: Block 1 — The 4-Level Hierarchy
Epic → Feature → User Story → Task
Notes: Frame the block: epic → feature → user story → task. Set context briefly, then move into the teaching content.

## Slide 6: 📚 ADO Vocabulary
These terms recur all day — including Work Item Query Language (WIQL), the query syntax.
Term
What it is
Work item
The atomic unit (Epic, Feature, User Story, Task, Bug)
Hierarchy
Epic → Feature → User Story → Task
Area path
Logical product area
Iteration path
Sprint / time window
State
New / Active / Resolved / Closed
Tags
Free-form labels for cross-cutting filters
Story points
Effort estimate (Fibonacci: 1, 2, 3, 5, 8, 13)
WIQL
Query language; saves filters
Notes: Read aloud. Get the vocabulary in muscle memory.

## Slide 7: 📚 The Hierarchy in Practice
Epic — strategic theme; ~1 per quarterly initiative ├── Feature — deliverable slice; 1–3 per Epic │ ├── User Story — user-visible value │ │ └── Task — engineering / design / TPM work │ └── User Story │ └── Task └── Feature
Don’t go deeper than 4 levels. Don’t promote a Task to a User Story to “make it visible.”
Notes: User Stories have user-visible value; tasks don’t. Coach this distinction.

## Slide 8: 📚 For Your Academy Feature
1 Epic — broader theme (e.g., “Reduce dispatcher after-shift admin load”)
1 Feature — your Product Requirements Document (PRD) (e.g., “Reconcile flow”)
5–10 User Stories — each acceptance criteria (AC) roughly maps to one
2–4 Tasks per User Story — Build / Test / Document / Review
Non-functional requirements (NFRs) from PRD Section 7 / Technical Concept Document (TCD) Section 3 Section 4 are work too. They get their own User Stories tagged non-functional.
Notes: NFRs are the most-skipped category in rookie backlogs.

## Slide 9: 👥 Activity 1 — Build the Hierarchy
Quads • 45 minutes
5 min: define the Epic (title + description + tags)
5 min: define the Feature (parent: Epic)
25 min: 5–10 User Stories from PRD Section 6 ACs
10 min: NFR stories tagged non-functional
⏱ 5 + 5 + 25 + 10
Notes: Watch for quads who skip NFRs entirely. Coach back.

## Slide 10: Block 2 — Field Discipline + Tasks
Title alone is not enough
Notes: Frame the block: title alone is not enough. Set context briefly, then move into the teaching content.

## Slide 11: 📋 Required Fields per Work Item
Field
Why it matters
Title
Clear, action-oriented
Description
1-paragraph context
Acceptance Criteria
From PRD Section 6; testable
Story Points
Effort estimate (User Stories only)
State
Workflow visibility
Area path
Reporting hierarchy
Iteration path
Sprint scheduling
Tags
Cross-cutting filters
Linked work items
Parent / child / related
Cost of skipping fields: sprint review where nobody can find anything.
Notes: 5 minutes per item to populate. Force it.

## Slide 12: 📊 Story Points (Fibonacci)
1, 2, 3, 5, 8, 13 — standard sequence
Use planning poker: each member estimates silently, then reveals. Discuss; don’t average.
Stories >13 points are too vague to estimate. Split.
Story points are a learning tool even when imperfect. Don’t skip because “we don’t really estimate.”
Notes: Estimation produces calibration over time. Even bad estimates beat no estimates.

## Slide 13: 📚 Tasks — Verb-First, Specific
For each User Story, draft 2–4 Tasks. Common pattern:
Build — the implementation work
Test — automated test coverage
Document — release notes, internal docs
Review — security, peer, stakeholder sign-off
Task title test: “Build Reconcile API endpoint” beats “API work.” Verb-first; specific.
Notes: Vague tasks don’t get done. They live forever.

## Slide 14: 👥 Activity 2 — Field Discipline + Tasks
Quads • 50 minutes
25 min: field pass on every work item
10 min: story-point estimation (planning poker)
15 min: 2–4 Tasks per User Story
⏱ 25 + 10 + 15
Notes: Stories with >13 points get split. Verb-first task titles.

## Slide 15: Block 3 — Queries + Boards
The 5 every team needs
Notes: Frame the block: the 5 every team needs. Set context briefly, then move into the teaching content.

## Slide 16: 🔎 The 5 Essential Queries
Query
When to run
Open in current sprint
Every standup
Blocked
Daily
Done in this sprint
End-of-sprint review
Stale (no movement > N days)
Weekly
Open NFRs / quality / compliance
Monthly
Save them in a shared folder. Name them clearly. They become the team’s heartbeat.
Notes: The “stale” query catches forgotten work — high-leverage for TPMs.

## Slide 17: 📚 Sprint Board + Kanban Board
Sprint board
Filtered to current iteration
Daily-standup view
Columns: To Do / In Progress / In Review / Done
Feature Kanban
Whole feature, not one sprint
Same columns
Used for cross-sprint planning
Set WIP limits explicitly (e.g., max 3 In Progress per developer). They are a forcing function.
Notes: Boards without WIP limits become aspirational lists.

## Slide 18: 👥 Activity 3 — Queries + Boards
Quads • 50 minutes
25 min: build all 5 queries
10 min: configure sprint board with WIP limits
10 min: configure Feature Kanban
5 min: identify the daily-driver query
⏱ 25 + 10 + 10 + 5
Notes: If WIP limits feel arbitrary, default: 3 per developer. Tune later.

## Slide 19: Block 4 — Reading the Charts + AI
CFD / burn-down / velocity, then AI as standup aid
Notes: Frame the block: cfd / burn-down / velocity, then ai as standup aid. Set context briefly, then move into the teaching content.

## Slide 20: 📊 The 3 Standard Charts
Chart
What it tells you
Cumulative Flow Diagram
Where work is queuing; cycle time; WIP bloat
Burn-down
On-track for end of sprint; scope creep
Velocity
Capacity over time; team-health signals
Watch: declining velocity is a flag for burnout, blockers, or context-switching. Investigate before pushing harder.
Notes: Charts are decision aids, not scorecards. Use them to ask questions, not assign blame.

## Slide 21: 🤖 AI as Standup-Prep Aid
Role: Standup-prep assistant for a TPM. Context: <yesterday's ADO query results — items moved state, items added, items closed, comments added> Task: Produce a 5-bullet standup summary: 1. Top 2 things shipped 2. Top 2 things blocked or stuck (>2 days no movement) 3. 1 anomaly (pattern unusual for this team) Constraints: - Use only the provided data - Flag anything you can't determine Format: 5 numbered bullets, each <15 words.
Validation discipline: cross-check claims against actual Azure DevOps (ADO) data. Same Wk 5 D5 rule.
Notes: Add to Pattern Library. Reusable.

## Slide 22: 👥 Activity 4 — Charts + AI Aid
Quads • 55 minutes • Wrap
25 min: walk the 3 charts; what would you look for?
10 min: run AI standup-prep prompt
10 min: validate output
10 min: document Section 2 with links / screenshots
⏱ 25 + 10 + 10 + 10 · 15-min wrap
Notes: Wrap-share: daily-driver query, WIP limit + why, expected hierarchy failure.

## Slide 23: 🎉 Day 2 Wrap
What we built
4-level hierarchy (Epic/Feature/Story/Task)
Field discipline applied
Story points + Tasks
5 essential queries
Sprint board + Kanban with WIP limits
Charts read; AI standup pattern
Delivery Plan (DP) Section 2 drafted
What opens tomorrow
Outcome-based vs output-based tracking
Tracking plan: output / outcome / leading indicator
Sprint cadence; dashboards
Bring to Day 3: Loaded ADO + DP Section 2. Tomorrow we wire tracking on top.
Notes: Round-robin close: each person says one ADO discipline they’ll personally enforce.

## Slide 24: 💬 Questions & Reflection
Which work item in your backlog is most likely to get forgotten?
Notes: Open the floor. Use the prompt — “Which work item in your backlog is most likely to get forgotten?” — to invite one short reflection per voice. Keep it tight; this is closure, not new content.