## Slide 1: 🧑‍🤝‍🧑 Stakeholder Mapping

## Slide 2: Week 6 • Day 1 • Stakeholder Alignment & Negotiation
TPM Academy
Notes: Welcome to Week 6. Outward-facing week. The artifacts you’ve shipped become inputs to real conversations.

## Slide 3: 🎯 Day 1 Objectives
Build a complete stakeholder list — not an org-chart copy
Place every stakeholder on a Power × Interest grid
Assign a RACI matrix (Responsible, Accountable, Consulted, Informed) to the 5 most consequential decisions, with one A per decision
Build a watch list — the high-power-low-interest stakeholders + their triggers
Draft Stakeholder Engagement Plan (SEP) Section 1 — the input to engagement planning tomorrow
Notes: By 16:00, every quad has SEP Section 1.

## Slide 4: 🕑 Today’s Shape
Clock
Block
Outcome
09:00 – 09:15
Opening
Pin TCD Section 6 sign-off matrix on the wall
09:15 – 10:30
Block 1 + Activity 1
Build the stakeholder list (the 5 circles)
10:45 – 12:00
Block 2 + Activity 2
Power × Interest mapping
13:00 – 14:15
Block 3 + Activity 3
RACI for 5 decisions
14:30 – 16:00
Block 4 + Activity 4 + Wrap
Watch list + SEP Section 1 polish
Notes: Arc: list → place → assign → watch.

## Slide 5: Block 1 — Build the List
Org chart ≠ stakeholder map
Notes: Frame Block 1: a complete stakeholder list is the foundation for every later step. Push quads to think beyond the org chart.

## Slide 6: 🎲 The Five Circles
Customer-facing: customer success, sales, support
Engineering-adjacent: architecture, security, platform, infra, data, QA
Operating partners: ops, IT, compliance, legal, finance
Decision-makers: PM lead, eng director, GM, executive sponsor
Indirect interest: other product teams whose work this touches
Most rookie lists are 5–7 names. A complete list is usually 10–18.
Notes: Push quads through all five circles. The omissions are usually compliance and finance.

## Slide 7: ✅ What Good Looks Like
Each stakeholder has a name (or named role) — not “the security team”
Each has a one-sentence concern — what they care about
Each has a relationship to this feature — consumer, owner, gate
Watch for: “TBD” entries. Force a name. The unowned stakeholder is the one who blindsides you.
Notes: Same discipline as the TCD Section 6 sign-off matrix.

## Slide 8: 👥 Activity 1 — Build the List
Quads • 45 minutes
5 min: copy from Technical Concept Document (TCD) Section 6
15 min: walk the 5 circles, augment
5 min: light cull
10 min: capture role + concern per stakeholder
⏱ 5 + 15 + 5 + 10
Notes: Lists below 8 mean a circle was missed.

## Slide 9: Block 2 — Power × Interest
Where each stakeholder lives
Notes: Pivot to placement: the 2×2 turns a list into a strategy. The argument over each placement is where the learning happens.

## Slide 10: 📊 The 2×2 Grid
High Power, High Interest
Manage closely — key partners; frequent deep engagement
Low Power, High Interest
Keep informed — engaged audience; you’ll learn from them
High Power, Low Interest
Manage with authority — the surprise-veto quadrant
Low Power, Low Interest
Monitor — low effort; periodic check-ins
The dangerous quadrant: high-power, low-interest. They surprise you with a “no” at the worst time.
Notes: Most TPMs over-invest in high-interest quadrants. The high-power-low-interest is what catches them.

## Slide 11: 📝 Worked Example (FieldPulse)
High-Interest, High-Power: Eng Lead Customer Success Lead QA Lead High-Interest, Low-Power: Other dispatcher squads Internal users testing Low-Interest, High-Power: Architect Eng Director Security Lead CFO Low-Interest, Low-Power: Internal communications Ops floor
Surprise: Compliance is low-interest in the abstract but high-power in specific moments (audit deadlines). Position can shift.
Notes: The “shifting” stakeholders are flagged for the watch list (Block 4).

## Slide 12: 👥 Activity 2 — Power × Interest
Quads • 50 minutes
5 min: sketch 2×2
15 min: place each stakeholder; argue when you disagree
10 min: name engagement style per quadrant
10 min: identify your 2 “surprises”
⏱ 5 + 15 + 10 + 10
Notes: The argument is the learning. Don’t average.

## Slide 13: Block 3 — RACI
One A per decision; if two, neither is
Notes: Block 3 introduces the accountability discipline. The “one A per decision” rule is the brutal check that surfaces ambiguity.

## Slide 14: 📚 RACI Refresher
Letter
Role
Definition
R
Responsible
Does the work. Many R’s possible.
A
Accountable
Owns the outcome. Exactly one per decision.
C
Consulted
Two-way; opinion sought.
I
Informed
One-way notification.
The discipline: if two people are A, neither is. If no one is A, the decision rots.
Notes: The “exactly one A” check is brutal but necessary.

## Slide 15: 🎯 The Five Decisions
Scope — what’s in vs out
Architecture — TCD Section 1 + key trade-offs
Service Level Objective (SLO) targets — TCD Section 4
Launch date — when it ships
Out-of-scope (OOS) backlog ownership — deferred items + owners
The TPM rookie error: “I’ll be A for architecture.” The architect is A. You’re C.
Notes: TPMs often grab too much A. Coach back to C where the architect or eng lead is the actual A.

## Slide 16: 📝 Worked RACI
Decision
R
A
C
I
Scope
TPM
PM Director
Eng Lead, Architect, CS
Sales, Support
Architecture
Architect
Eng Director
TPM, Security, Platform
All eng
SLO targets
Eng Lead
TPM
SREs, CS
Eng Director
Launch date
TPM
PM Director
Eng Lead, CS, Marketing
All eng, Sales
OOS backlog
TPM
TPM
Eng Lead
Backlog readers
Notes: Walk down the A column: 5 unique A’s, no duplicates. That’s the check.

## Slide 17: 👥 Activity 3 — RACI for 5 Decisions
Quads • 50 minutes
20 min: draft matrix
5 min: “no two A’s” check
10 min: “is the A actually empowered?” check
5 min: “anyone surprised by being I?”
⏱ 20 + 5 + 10 + 5
Notes: The “actually empowered” check is the most useful. Many nominal A’s are rubber stamps.

## Slide 18: Block 4 — Watch List + Polish
The early-warning system
Notes: Final block: the watch list converts mapping into vigilance. Each high-power-low-interest stakeholder gets a named trigger.

## Slide 19: 👁️ The Watch List
For each high-power-low-interest stakeholder, identify the event that would move them to high-interest — and the trigger to escalate engagement.
Stakeholder
Trigger to escalate
CFO
Cost projection > $X
General Counsel
Any regulator email
Chief Customer Officer
Top-10 customer escalation
Architect
Architecture stance changes after Day 1
The watch list is your early-warning system. Distinguishes managers of stakeholders from reactors to them.
Notes: 3–5 entries on the watch list, with specific triggers, is the goal.

## Slide 20: 🤖 Day 1 AI Prompt
Role: Senior PM coaching a junior TPM on stakeholder management. Context: <stakeholder list with quadrants and RACI> Task: Identify 3 likely blind spots: 1. A stakeholder who probably has more power than the map shows 2. A decision where the A is wrong or absent 3. A high-power-low-interest stakeholder whose trigger isn't named Constraints: - Be specific to names and roles given - Do not invent stakeholders Format: 3 numbered findings, each with one-sentence rationale.
Notes: Add to Pattern Library. Reusable for future feature stakeholder mapping.

## Slide 21: 👥 Activity 4 — Watch List + Polish
Quads • 55 minutes • Wrap
15 min: polish Section 1
20 min: build watch list (3–5 stakeholders + triggers)
5 min: cross-check vs TCD Section 6
5 min: AI prompt + provenance note
⏱ 15 + 20 + 5 + 5 · 15-min wrap
Notes: Wrap-share: 1 contested placement, 1 reassigned A, 1 watch-list trigger.

## Slide 22: 🎉 Day 1 Wrap
What we built
Comprehensive stakeholder list
Power × Interest grid
RACI for 5 decisions
Watch list with triggers
SEP Section 1 drafted
What opens tomorrow
Managing engagement for outcomes
Per-stakeholder engagement plans
Cadence + format + asks
Bring to Day 2: SEP Section 1. Tomorrow we plan the actual engagement.
Notes: Round-robin close: each person says one stakeholder they realized today they had wrongly placed.

## Slide 23: 💬 Questions & Reflection
Whose attention have you been spending too much on? Too little?
Notes: Open the floor. Encourage quads to share one stakeholder whose placement on the map surprised them today.