## Slide 1: 🎯 Lean Delivery & Value Stream Mapping

## Slide 2: Week 7 • Day 4 • Agile Delivery & ADO Mastery
TPM Academy
Week 7 builds Agile delivery and Azure DevOps (ADO) mastery.
Notes: Today: look at the system that produces the work. Most teams optimize the wrong step because they’ve never seen the whole stream.

## Slide 3: 🎯 Day 4 Objectives
Identify the value stream from idea to value-realized (7–10 steps)
Measure or estimate process time, lead time, and flow efficiency per step
Find the top 3 queues with named cause + candidate intervention
Draw the visual VSM
Use AI to surface non-obvious queues
Notes: By 16:00, every quad has DP Section 4.

## Slide 4: 🕑 Today’s Shape
Clock
Block
Outcome
09:00 – 09:15
Opening
Pin DP Sections 1–3
09:15 – 10:30
Block 1 + Activity 1
Identify your value stream
10:45 – 12:00
Block 2 + Activity 2
Measure or estimate each step
13:00 – 14:15
Block 3 + Activity 3
Top 3 queues
14:30 – 16:00
Block 4 + Activity 4 + Wrap
VSM + AI critique
Notes: Arc: identify → measure → queue-find → visual.

## Slide 5: Block 1 — The Lean Claim
Most of the time, work is waiting
Notes: Frame the block: most of the time, work is waiting. Set context briefly, then move into the teaching content.

## Slide 6: 📚 Lean’s Foundational Claim
Most of the time work spends in a system is waiting, not being worked on. Reduce waiting; reduce total time.
Typical software example: a story with 2 hours of actual coding may spend 3 weeks in the system — waiting for spec, review, QA, deploy slot, merge.
A TPM who optimizes coding time saves minutes. A TPM who reduces the waiting saves weeks.
Notes: This is the entry point. Don’t soften it.

## Slide 7: 📚 VSM Vocabulary
Term
Meaning
Value stream
Whole flow from idea to value-realized
Process time (PT)
Hands-on-work time at a step
Lead time (LT)
Total time at a step including waiting
Flow efficiency
PT / LT × 100%
Queue
Work waiting between steps
Cycle time
Lead time across the whole stream
Throughput
Completed items per unit time
WIP
Items currently being worked
Little’s Law
Cycle time = WIP / throughput
Notes: Flow efficiency is the most-startling number. Single-digit % is typical.

## Slide 8: 📚 Typical Software Value Stream
Idea → Discovery → Spec → Build → Ship → Measure → Iterate │ │ │ │ │ │ │ ▼ ▼ ▼ ▼ ▼ ▼ ▼ Q1 Q2 Q3 Q4 Q5 Q6 Q7
Worst queues for most teams:
Spec → Build (waiting for engineering capacity)
Build → Ship (review, QA, deploy slot)
Ship → Measure (data accumulation; nobody looks)
Notes: The queues hide the time.

## Slide 9: 👥 Activity 1 — Identify Your Stream
Quads • 45 minutes
15 min: walk steps idea → value-realized
10 min: identify queues between steps
10 min: mark step boundaries explicitly
⏱ 15 + 10 + 10
Notes: Aim for 7–10 steps. Owner per step is a role (sometimes a name).

## Slide 10: Block 2 — Measure or Estimate
Process time / lead time / flow efficiency
Notes: Frame the block: process time / lead time / flow efficiency. Set context briefly, then move into the teaching content.

## Slide 11: 📊 Worked Numbers (FieldPulse)
Step
PT
LT
Flow eff
Idea
1 hr
3 days
5%
Discovery
4 hrs
2 days
25%
Spec
16 hrs
2 weeks
22%
Estimate + accept
1 hr
1 week
3%
Build
8 hrs/story
1 week/story
14%
Code review
30 min
1.5 days
4%
QA + integration
4 hrs
2 days
12%
Deploy
30 min
6 hrs
8%
Total cycle time: 6–8 weeks. Total flow efficiency: 5–15% typical.
Notes: If a quad refuses to estimate, push: “honest guess beats no number.” Calibrate over time.

## Slide 12: 👥 Activity 2 — Measure / Estimate
Quads • 50 minutes
40 min: PT + LT + flow eff per step
⏱ 50 min straight
Notes: Push numbers. Label estimates as estimates. Compute flow efficiency.

## Slide 13: Block 3 — Top 3 Queues
Find where the time hides
Notes: Frame the block: find where the time hides. Set context briefly, then move into the teaching content.

## Slide 14: 🔎 Queue Investigation
For each top queue:
Why does this queue exist? (capacity, policy, inertia, hidden dependency)
What would shrink it? (capacity, policy change, parallel work, dependency removal)
Cost of shrinking? (people-time, money, organizational change)
“We’re slow in code review” is not specific. “PRs wait 2 days for first review because we have 8 reviewers and 40 PRs/week” is.
Notes: Force specificity. Vague queues don’t get fixed.

## Slide 15: 📝 Worked Top 3 Queues
Queue
Cause
Intervention candidate
Spec → Estimate (1 wk)
Sprint planning bi-weekly
Mid-cycle sync; mid-sprint pull
Build → Code review (1.5 d)
5 reviewers; PRs wait
Pair-review during dev; auto-assign
Discovery → Spec (varies)
Customer interview scheduling
Async cycles; lighter-weight discovery for known patterns
Notes: Each candidate intervention is an experiment for tomorrow.

## Slide 16: 👥 Activity 3 — Top 3 Queues
Quads • 50 minutes
5 min: sum total queue time
10 min: identify top 3 queues
15 min: investigate each (cause / intervention / cost)
10 min: rank by impact / effort / risk
⏱ 5 + 10 + 15 + 10
Notes: “Necessary delay” (e.g., 30 days for outcome data) ≠ queue waste. Distinguish.

## Slide 17: Block 4 — Visual VSM + AI
One page; the queues hit emotionally
Notes: Frame the block: one page; the queues hit emotionally. Set context briefly, then move into the teaching content.

## Slide 18: 📝 The VSM Canvas
[Step 1]──→[Step 2]──→[Step 3]──→... │ │ │ PT: __ PT: __ PT: __ LT: __ LT: __ LT: __ QUEUE QUEUE QUEUE __ items __ items __ items __ days __ days __ days ═════════════════════════════════════ Total cycle time: __ days Total process time: __ days Total flow efficiency: __%
Notes: One page. Whiteboard or paper. The visual makes the queues hit.

## Slide 19: 🤖 AI Critique Prompt
Role: Lean coach reviewing a software value stream. Context: <description of the VSM with PT/LT/flow eff numbers and identified queues> Task: Identify 3 queues likely missing or under-counted: 1. A queue between two steps not yet shown 2. A step where PT and LT seem out of line with team reality 3. An invisible queue (e.g., approvals, "ping someone") Constraints: - Use only the data given - Be specific Format: 3 numbered findings — what's missing / why suspect / how to verify.
Notes: Add to Pattern Library.

## Slide 20: 👥 Activity 4 — VSM + AI
Quads • 55 minutes • Wrap
20 min: draw the VSM
10 min: AI critique
10 min: update VSM; recompute flow efficiency
5 min: document in Section 4
⏱ 20 + 10 + 10 + 5 · 15-min wrap
Notes: Wrap-share: flow efficiency, biggest queue, non-obvious queue.

## Slide 21: 🎉 Day 4 Wrap
What we built
Value stream identified
PT / LT / flow efficiency per step
Top 3 queues with cause + intervention
Visual VSM
Delivery Plan (DP) Section 4 drafted
What opens tomorrow
Bottleneck removal experiments
Hypothesis / test / success criterion
Friday: full DP integration + sign-off
Bring to Day 5: DP Sections 1–4 + your top 3 queues. Tomorrow we design the experiments.
Notes: Round-robin close: each person says one queue they’d attack first.

## Slide 22: 💬 Questions & Reflection
Where does your team’s time hide that nobody talks about?
Notes: Open the floor. Use the prompt — “Where does your team’s time hide that nobody talks about?” — to invite one short reflection per voice. Keep it tight; this is closure, not new content.